## Instructie
Manual
Think before you act, do not remove formulas from the sheets ( check first )
First use
| Fill in the Project, Class and Team name in sheet Total | Vul de naam van het project en de klas en groep in op de tab "Totaal"
| Fill in the usernames for the students, remove unused names | Daarna eveneens de namen van de 4 studenten
Need more activity lines in some week |  | Meer activiteitregels nodig in een week?
| Copy the last line and insert it before the total line | Maak een kopie van de laatste activiteitregel en voeg deze in voor de totaalregel

## Total
Time registration |  | Students | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Total
Project : | Project Client on Board | Jafar Alirahmi | 12.5 | 12 | 12.5 | 15.5 | 15 | 23 | 0 | 0 | 90.5
|  | Viktor Krastev | 6 | 10 | 11 | 11 | 27 | 28 | 0 | 0 | 93
Class & Team | DHI2V.Sp & Group 3 | Justin Fuchs | 7 | 6.25 | 0 | 0 | 0 | 0 | 0 | 0 | 13.25
|  | Rubén Gómez | 7 | 6.5 | 9.5 | 8.7 | 9.5 | 14 | 0 | 0 | 55.2
|  | Yaroslav Peptiuk | 11.5 | 9.25 | 11.5 | 12 | 9.5 | 14 | 0 | 0 | 67.75
|  | Aleks Proskurkin | 12 | 11.75 | 12.5 | 17 | 12 | 13.5 | 14.5 | 0 | 93.25
|  | Ferhat Kelten | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 24
|  | Weektotal | 56 | 67.75 | 69 | 64.2 | 73 | 92.5 | 14.5 | 0
|  | Sprinttotal |  | 123.75 |  | 133.2 |  | 165.5 |  | 14.5
|  | Hours to burn | 616 | 548.25 | 479.25 | 415.05 | 342.05 | 249.55 | 235.05 | 235.05
Available hours per week : | 84 | Total Hours available | 672 | 588 | 504 | 420 | 336 | 252 | 168 | 84

## Week (1)
Week 1 | Uren TOTAAL
Jafar Alirahmi | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff |  | 2.5 |  |  |  |  | 2.5
Second Meeting-PoA |  |  |  | 2 |  |  | 2
Create requirements |  |  |  |  | 2 |  | 2
Edit/Add more requirements | [5 empty] | 4 | 4
ScrumDoc-DoD | [5 empty] | 2 | 2
Total | 0 | 2.5 | 0 | 2 | 2 | 6 | 12.5
Viktor Krastev | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff |  | 2.5 |  |  |  |  | 2.5
Second class |  |  |  |  | 2 |  | 2
Create requirements |  |  |  | 1.5 |  |  | 1.5
0
0
Total | 0 | 2.5 | 0 | 1.5 | 2 | 0 | 6
Justin Fuchs | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff |  | 2.5 |  |  |  |  | 2.5
Second class |  |  |  | 2.5 |  |  | 2.5
create CoC |  |  |  | 2 |  |  | 2
0
0
Total | 0 | 2.5 | 0 | 4.5 | 0 | 0 | 7
Rubén Gómez | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff |  | 2.5 |  |  |  |  | 2.5
Second Class |  |  |  | 2.5 |  |  | 2.5
Requeriments |  |  |  |  | 2 |  | 2
0
0
Total | 0 | 2.5 | 0 | 2.5 | 2 | 0 | 7
Yaroslav Peptiuk | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff |  | 2.5 |  |  |  |  | 2.5
Requirements |  |  | 1 |  |  |  | 1
Documentation |  |  | 3 |  |  |  | 3
Wireframes |  |  | 1 |  |  |  | 1
TypeScript tutorials |  |  |  | 2 | 2 |  | 4
Total | 0 | 2.5 | 5 | 2 | 2 | 0 | 11.5
Aleks Proskurkin | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff |  | 2.5 |  |  |  |  | 2.5
Requirements |  |  | 1 |  |  |  | 1
Documentation |  |  | 6 |  |  |  | 6
Second class |  |  |  |  | 2.5 |  | 2.5
0
Total | 0 | 2.5 | 7 | 0 | 2.5 | 0 | 12
Ferhat Kelten | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Week (2)
Week 2 | Uren TOTAAL
Jafar Alirahmi | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
R&D and Added typescript and svelte to the source code | 2 | [5 empty] | 2
Editing requirements |  | 2 |  |  |  |  | 2
Team meeting |  |  | 2 |  |  |  | 2
Team meeting, Finalize requirements |  |  |  | 2 |  |  | 2
End sprint meeting, Team plan, Finalize Documents | [5 empty] | 4 | 4
Total | 2 | 2 | 2 | 2 | 0 | 4 | 12
Viktor Krastev | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Meeting with client |  | 1.5 |  |  |  |  | 1.5
Second class |  |  |  | 2 |  |  | 2
Note wrong/duplicate requirements |  | 1.5 |  |  |  |  | 1.5
Wednesday meeting, editing requirements |  |  | 1.5 |  |  |  | 1.5
Finalize sprint 1 meeting on saturday | [5 empty] | 4 | 4 | ч
Total | 0 | 3 | 1.5 | 2 | 0 | 4 | 10.5
Justin Fuchs | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Meeting with client |  | 1.5 |  |  |  |  | 1.5
class 2 |  |  |  | 2.25 |  |  | 2.25
Meeting 1 |  |  | 1.5 |  |  |  | 1.5
starting DB design |  |  |  |  | 1 |  | 1
0
Total | 0 | 1.5 | 1.5 | 2.25 | 1 | 0 | 6.25
Rubén Gómez | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Meeting with client |  | 1.5 |  |  |  |  | 1.5
No second class, I had another class | [6 empty] | 0
Wednesday meeting, editing requirements |  |  | 1.5 |  |  |  | 1.5
Business Requirements |  |  | 1.5 |  |  |  | 1.5
Finalize sprint 1 meeting on saturday | [5 empty] | 2 | 2
Total | 0 | 1.5 | 3 | 0 | 0 | 2 | 6.5
Yaroslav Peptiuk | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Meeting with client | [6 empty] | 1.5
Second class | [6 empty] | 2.25
Non-functional and functional requirements | [6 empty] | 2
Stand-up meeting | [6 empty] | 1.5
Finalize first deliverable (editining .md requirements table + backlog) | [6 empty] | 2
Total | 0 | 0 | 0 | 0 | 0 | 0 | 9.25
Aleks Proskurkin | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Meeting with client |  | 2.5 |  |  |  |  | 2.5
Second class |  |  |  | 2.25 |  |  | 2.25
Functional requirements |  |  |  |  | 4 |  | 4
Stand-up meeting |  |  | 1.5 |  |  |  | 1.5
Stand-up meeting (finalizing first deliverable) | [5 empty] | 1.5 | 1.5
Total | 0 | 2.5 | 1.5 | 2.25 | 4 | 1.5 | 11.75
Ferhat Kelten | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Analyzing the assignment / First 2 classes |  | 2.5 |  | 2.5 |  |  | 5
Meeting with Client |  | 1.5 |  |  |  |  | 1.5
Third class |  |  |  | 1 |  |  | 1
Business Requirements |  | 1.5 |  | 1 |  |  | 2.5
Editing documentation | [5 empty] | 2 | 2
Total | 0 | 5.5 | 0 | 4.5 | 0 | 2 | 12
#REF! | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Week (3)
Week 3 | Uren TOTAAL
Jafar Alirahmi | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Added Button comonent | 1 | [5 empty] | 1
Sprints page, US #3 |  |  | 3 |  |  | 3 | 6
Refactor the front-end and switch to JS instead of TS |  |  |  |  | 1 |  | 1
Team meeting |  | 2.5 |  |  |  |  | 2.5
Team meeting |  |  |  | 2 |  |  | 2
Total | 1 | 2.5 | 3 | 2 | 1 | 3 | 12.5
Viktor Krastev | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Class one |  | 2.5 |  |  |  |  | 2.5
Class two |  |  |  | 2 |  |  | 2
Create new wireframes |  |  | 1.5 |  |  |  | 1.5
Test case page, issue #9 | 1.5 | [5 empty] | 1.5
Side menu, issue #97 |  |  | 1 | 1 |  | 1.5 | 3.5
Total | 1.5 | 2.5 | 2.5 | 3 | 0 | 1.5 | 11
Justin Fuchs | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rubén Gómez | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
First class |  | 2.5 |  |  |  |  | 2.5
Second class |  |  |  | 2.5 |  |  | 2.5
Test case frontend |  |  | 2 |  |  | 2.5 | 4.5
0
0
Total | 0 | 2.5 | 2 | 2.5 | 0 | 2.5 | 9.5
Yaroslav Peptiuk | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Class one |  | 2.5 |  |  |  |  | 2.5
Class two |  |  |  | 2 |  |  | 2
Improve wireframes | 1 | 1 |  |  |  |  | 2
Database design |  |  | 2 | 1 |  |  | 3
Database queries |  |  |  | 1 | 1 |  | 2
Total | 1 | 3.5 | 2 | 4 | 1 | 0 | 11.5
Aleks Proskurkin | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
First class |  | 2.25 |  |  |  |  | 2.25
Second class |  |  |  | 2.25 |  |  | 2.25
Test case page |  |  |  |  | 4 |  | 4
Documentation | 2 |  |  |  |  | 2 | 4
0
Total | 2 | 2.25 | 0 | 2.25 | 4 | 2 | 12.5
Ferhat Kelten | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Creating database |  |  |  |  | 2 | 3 | 5
Creating token | [5 empty] | 3 | 3
Creating API calls | [5 empty] | 4 | 4
0
0
Total | 0 | 0 | 0 | 0 | 2 | 10 | 12
#REF! | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Week (4)
Week 4 | Uren TOTAAL
Jafar Alirahmi | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Login page and token and user store,US #8 |  |  | 4 |  |  |  | 4
Team meeting |  | 2.5 |  |  |  |  | 2.5
Team meeting |  |  |  | 2 |  |  | 2
Dashboard Page-front end , US#6 | 4 | [5 empty] | 4
client meeting |  |  |  |  | 1
Edit sprint page, US #3 | [5 empty] | 2 | 2
Total | 4 | 2.5 | 4 | 2 | 1 | 2 | 15.5
Viktor Krastev | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Class one and two |  | 2.5 |  | 2.5 |  |  | 5
NF-02 #107 | 1.5 | [5 empty] | 1.5
FR-16 #108 |  |  | 3 |  |  |  | 3
Client meeting |  |  |  |  | 0.5 |  | 0.5
Finalize project for Deliverable Sprint 1 | [5 empty] | 1 | 1
Total | 1.5 | 2.5 | 3 | 2.5 | 0.5 | 1 | 11
Justin Fuchs | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rubén Gómez | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
First class(later I has an Exam) |  | 1.5 |  |  |  |  | 1.5
Second class |  |  |  | 2.5 |  |  | 2.5
Client meeting |  |  |  |  | 0.5 |  | 0.5
Scrum master | [5 empty] | 0.2 | 0.2
FR07 - System allow users to attach files to test cases. |  |  | 2 |  |  | 2 | 4
Total | 0 | 1.5 | 2 | 2.5 | 0.5 | 2.2 | 8.7
Yaroslav Peptiuk | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
First and second class |  | 2.5 |  | 2.5 |  |  | 5
Database queries |  |  | 1 |  |  |  | 1
Dummy data for db |  |  | 1 |  |  |  | 1
Client meeting changes |  |  |  |  | 1 |  | 1
Wireframes and refactoring |  |  | 1 | 1 | 2 |  | 4
Total | 0 | 2.5 | 3 | 3.5 | 3 | 0 | 12
Aleks Proskurkin | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
First class |  | 2.25 |  |  |  |  | 2.25
Second class |  |  |  | 2.25 |  |  | 2.25
Web socket noltification |  |  |  |  | 2.5 | 2 | 4.5
Test page | 3 |  | 5 |  |  |  | 8
0
Total | 3 | 2.25 | 5 | 2.25 | 2.5 | 2 | 17
Ferhat Kelten | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Week (5)
Week 5 | Uren TOTAAL
Jafar Alirahmi | Uren
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Team meeting |  | 2.5 |  |  |  |  | 2.5
Team meeting |  |  |  | 2.5 |  |  | 2.5
Sprint Backend |  |  | 2 |  | 4 |  | 6
fix bugs and refactor | 2 |  |  |  |  | 2 | 4
Total | 2 | 2.5 | 2 | 2.5 | 4 | 2 | 15
Viktor Krastev | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Class one and two |  | 2.5 |  | 2.5 |  |  | 5
FR-17 #109 | 4 | [5 empty] | 4
FR-18 #113 |  | 8 | 2 |  |  |  | 10
FR-18 BI1 #114 |  |  | 2 |  |  |  | 2
NF-03 #115 |  |  | 3 | 3 |  |  | 6
Total | 4 | 10.5 | 7 | 5.5 | 0 | 0 | 27
Justin Fuchs | Uren
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rubén Gómez | Uren
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
First class |  | 2.5 |  |  |  |  | 2.5
Second Class |  |  |  | 2.5 |  |  | 2.5
FR07 | 1 |  |  |  | 2 |  | 3
Prepare/learning everything for the database |  |  | 1.5 |  |  |  | 1.5
0
Total | 1 | 2.5 | 1.5 | 2.5 | 2 | 0 | 9.5
Yaroslav Peptiuk | Uren
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Class one |  | 2.5 |  |  |  |  | 2.5
Class two |  |  |  | 2 |  |  | 2
Frontend design sharing |  |  | 2 |  | 1 | 2 | 5
0
0
Total | 0 | 2.5 | 2 | 2 | 1 | 2 | 9.5
Aleks Proskurkin | Uren
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
First class |  | 2.25 |  |  |  |  | 2.25
Second class |  |  |  | 2.25 |  |  | 2.25
Styling Test Page |  |  |  |  | 2.5 | 2 | 4.5
Backend fix for Tests | [5 empty] | 3 | 3
0
Total | 0 | 2.25 | 0 | 2.25 | 2.5 | 5 | 12
Ferhat Kelten | Uren
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | Uren
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | Uren
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | Uren
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Week (6)
Week 6 | Uren TOTAAL
Jafar Alirahmi | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Team meeting |  | 2.5 |  |  |  |  | 2.5
Team meeting |  |  |  | 2.5 |  |  | 2.5
SprintInfo component |  |  | 4 |  |  |  | 4
Sprints Detail page | 4 | 2 |  |  |  |  | 6
Fixed bugs and refactor |  |  |  |  | 2 | 2 | 4
CSS for sprint page and sprint details | [5 empty] | 4 | 4
Total | 4 | 4.5 | 4 | 2.5 | 2 | 6 | 23
Viktor Krastev | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
US-08 BI-1 | 2 | 3 |  | 2 | 5 | 8 | 20
Class one and two |  | 2.5 |  | 2.5 |  |  | 5
FR-19 |  |  |  |  | 1 | 2 | 3
0
0
Total | 2 | 5.5 | 0 | 4.5 | 6 | 10 | 28
Justin Fuchs | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rubén Gómez | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
First Class |  | 2.5 |  |  |  |  | 2.5
Second Class |  |  |  | 2.5 |  |  | 2.5
Dashboard |  |  | 2 |  |  | 4 | 6
Learn chart.js |  |  |  |  | 3 |  | 3
0
Total | 0 | 2.5 | 2 | 2.5 | 3 | 4 | 14
Yaroslav Peptiuk | Hours
User story / task description |  | Di | Wo | Do | Vr | Za/Zo | Total
Class one |  | 2.5 |  |  |  |  | 2.5
Class two |  |  |  | 2 |  |  | 2
Frontend Styling |  |  | 1.5 |  | 1 |  | 2.5
Test case page fixes |  |  |  | 4 | 3 |  | 7
0
Total | 0 | 2.5 | 1.5 | 6 | 4 | 0 | 14
Aleks Proskurkin | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
First class |  | 2.25 |  |  |  |  | 2.25
Second class |  |  |  | 2.25 |  |  | 2.25
Test case details backend side |  |  |  |  | 3 | 1 | 4
Test case page front end |  |  |  |  | 4 | 1 | 5
0
Total | 0 | 2.25 | 0 | 2.25 | 7 | 2 | 13.5
Ferhat Kelten | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Week (7)
Week 7 | Uren TOTAAL
Jafar Alirahmi | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Viktor Krastev | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Justin Fuchs | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rubén Gómez | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yaroslav Peptiuk | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Aleks Proskurkin | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
First class |  | 2.25 |  |  |  |  | 2.25
Second class |  |  |  | 2.25 |  |  | 2.25
FR22 |  |  | 5 |  |  |  | 5
US02 |  |  |  |  | 3 | 2 | 5
0
Total | 0 | 2.25 | 5 | 2.25 | 3 | 2 | 14.5
Ferhat Kelten | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Week (8)
Week 8 | Uren TOTAAL
Jafar Alirahmi | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Viktor Krastev | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Justin Fuchs | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rubén Gómez | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yaroslav Peptiuk | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Aleks Proskurkin | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ferhat Kelten | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0